## Sheet1
Project: Movie Manager Application
Project Backlog
| Backlog Items | % Complete | Estimated Programming Time (HH:MM) | Actual Programming Time (HH:MM) | Estimated Difficulty (1 to 10) | Actual Difficulty (1 to 10)
Project:
| Create Windows Forms Application | 100% | 2:30 | 1:45 | 4 | 5
Main.cs Form:
| Create Main.cs | 100% | 0:10 | 0:50 | 1 | 1
| Add working MenuStrip control having all menu items | 100% | 0:15 | 0:10 | 1 | 1
| Add DataGridView control and write code to populate with movies list when the form first starts | 100% | 1:00 | 0:25 | 5 | 3
| Write code for Refresh menu item to populate DataGridView control on-demand | 100% | 1:00 | 1:30 | 8 | 7
About.cs Form:
| Create About.cs form. Test that it can be invoked from Main menu, and that it can be invoked as a dialogue | 100% | 0:05 | 0:10 | 1 | 1
| Add required text to RichTextBox control and code content display | 100% | 0:15 | 0:30 | 4 | 3
AddMovie.cs Form:
| Create AddMovie.cs form. Test that is can be invoked from Main menu | 100% | 0:01 | 0:08 | 1 | 1
| Code AddMovie to add new title to database. | 100% | 1:10 | 1:30 | 7 | 5
UpdateMovie.cs Form:
| Create UpdateMovie.cs form. Test that it can be invoked from Main menu | 100% | 0:05 | 0:15 | 1 | 1
| Code UpdateMovie's Find button to test whether a movie of a given title exists. | 100% | 0:30 | 0:45 | 5 | 5
| Code logic to fill-in controls on form with Movie data | 100% | 0:30 | 0:50 | 4 | 3
| Code logic to update/save changes to movie row in database. | 100% | 0:45 | 1:10 | 7 | 5
DeleteMovie.cs Form:
| Create DeleteMovie.cs form. Test that it can be invoked from Main menu | 100% | 0:05 | 0:15 | 1 | 1
| Test DeleteMovie's Find button to test whether a movie of a given title exists. | 100% | 0:30 | 1:10 | 7 | 6
| Code logic to prompt user with dialogue box asking if they really wish to delete title. | 100% | 0:05 | 1:55 | 6 | 5
| Code logic to delete movie from from database. | 100% | 0:15 | 0:45 | 4 | 4
|  | Total Time: | 9:11 | 14:03